PROGRAM CLOSEOUT MEMO

Project Helena — Closeout

Cost-optimisation program — outcome, root causes, and what we learned

| Program | Project Helena — Group Cost Optimisation |
| --- | --- |
| Sponsor | David Chen, VP Operations |
| Status | Closed — target missed |
| Reporting period | FY27 Q1 |
| Classification | Confidential — Internal Only |

# Headline

What happened, in one paragraph Helena set an ambitious savings target and delivered well short of it. The uncomfortable part is that the governance layer held — cadence, tracking and reporting all worked as designed. The shortfall came from inside the individual workstreams, and most of it for reasons outside the program’s direct control. The miss is concentrated in EMEA, with the UK the single largest affected market. None of it reflects a deterioration in the underlying business — it is a cost program that ran into single points of failure.

# Workstream results

Outcomes are shown qualitatively; the savings figures sit in the finance model and the program tracker.

| Workstream | Outcome | What happened |
| --- | --- | --- |
| Procurement | Missed | The Vantage renegotiation collapsed — the supplier walked late in the process. Re-tender yields no benefit this year. |
| SG&A | Missed | Planned savings were absorbed by mandatory CSRD compliance hiring — an obligation that arrived mid-program. |
| Real estate | Missed | The Frankfurt consolidation was delayed by a failed fire sign-off; the savings shift into next year rather than disappear. |
| Technology | Partial | The ERP migration slipped a cycle; the associated benefits move into the next period. |

# Root causes — what went wrong

- Procurement: we hung the biggest single saving on one supplier renegotiation, with no fallback. When their team changed and the deal reset, we had no leverage and no plan B.

- SG&A: an unplanned regulatory obligation (CSRD) absorbed the savings. We carried no contingency for it.

- Real estate: the Frankfurt move slipped on a handover and inspection issue — a timing failure, not an overspend.

- Technology: the ERP migration moved to the next cycle, taking its benefits with it.

# Retrospective — what we learned

A candid post-mortem from the program team. Recorded here deliberately, in plain language, because the lessons matter more than the closing number — and because they will shape whatever comes next.

The honest read is that Helena was well run but built on optimistic assumptions. Governance was never the problem. Three of the four workstreams missed because of single points of failure we would have caught with more challenge up front. We ran the program tightly; we scoped it hopefully.

- We over-concentrated the target. Too much of it rode on one supplier renegotiation. There was no second option kept warm, so when it fell over we had nothing to fall back on.

- We treated savings as banked too early. A handshake and an uncountersigned draft were enough for us to put the number in the plan. They shouldn’t have been.

- We assumed timelines we didn’t control. A single inspection failure in Frankfurt was enough to move a year’s savings. We had no slack for it.

- We carried no reserve for regulatory cost. When CSRD landed, it went straight to the bottom line because nothing was set aside to absorb it.

None of these are signs of a weak business. They are execution and assumption failures on a cost program — which is exactly why the headline numbers read worse than the operational reality. That distinction has to be made explicitly when this goes to leadership.

# Recommendation

Launch “Helena II” to pursue the unrealised savings across the next two years — but with the lessons above built in: tighter challenge on assumptions, supplier fallbacks kept warm, real-estate timelines de-risked, and an explicit contingency reserve for regulatory and handover risk.

- Reforecast first. Make sure leadership sees the one-off drivers separated from the single structural item (CSRD) before any decisions are taken on the back of the headline.

- Govern the metric. “Operating cost ratio by market” is calculated differently by finance and ops today. Define it once, in the model, so future programs argue about the problem and not the number.

Closeout memo for internal review. Savings and variance figures are held in the finance model and program tracker; this memo is the qualitative record of why the program landed where it did.